NET3006A Project Proposal — ML for Network Telemetry

1. Team Members

- Abdul Rehman

- Esam Mukbil

- Hashim Kshim

2. Project Option

Option 1: Survey / Reading Project

The team will survey and synthesize recent academic and industry literature on the use of machine learning for network telemetry.

3. Topic

Topic 2 – ML for Network Telemetry

Machine learning methods are increasingly being applied to automatically extract insights from high-volume, fine-grained network measurement data — such as flow statistics, packet traces, and in-band telemetry. This enables real-time anomaly detection, performance prediction, and autonomous network optimization. Our survey will examine how state-of-the-art ML techniques are applied across these sub-problems in modern network telemetry pipelines.

4. Project Objective

The objective of this project is to explore and synthesize the current state of research and industry practice in applying machine learning to network telemetry. Specifically, the team will: (1) identify and categorize the primary ML methods used (e.g., supervised, unsupervised, deep learning), (2) map them to specific network telemetry tasks such as anomaly detection, traffic prediction, and QoS optimization, and (3) identify open challenges and emerging trends in the field, particularly in the context of 5G/6G and next-generation network architectures.

5. Steps, Timeline, and Task Division

| Step / Milestone | Target Date | Responsible Member |
| --- | --- | --- |
| Topic scoping & initial paper search | Week 1 (Mar. 10–14) | All members |
| Read & annotate 2–3 papers each | Week 2 (Mar. 17–21) | Abdul, Esam, Hashim |
| Synthesize findings & outline presentation | Week 3 (Mar. 24–28) | All members |
| Draft presentation slides (each member's section) | Week 4 (Mar. 31–Apr. 4) | Each member owns their slides |
| Internal rehearsal & Q&A prep | Week 5 (Apr. 7–11) | All members |
| Final submission of slides on Brightspace | Night before presentation | Abdul (submitter) |

Task Division Summary:

- Abdul Rehman: ML methods for anomaly detection in telemetry; submission logistics

- Esam Mukbil: ML for performance prediction and QoS optimization

- Hashim Kshim: Industry implementations (Nokia, Ericsson) and emerging trends (6G, GenAI for telemetry)